## Form responses 1
Column 1 | PO Number | Vendor Name | Quantity | Location
2026-05-08 12:43 | 001 | Kajal | 100 | Bangalore
2026-05-08 14:11 | 002 | moni | 10 | Dhanbad
2026-05-08 17:35 | 1 | rajesh | 5000 | ben
2026-05-09 09:53 | 003 | vinay | 200 | jharkhand
2026-05-09 10:11 | 004 | moni | 10 | Rajajinagar

## FMS
2026-05-11 15:47
What | Generate PO and Fill Google Form |  |  |  | Issue PO To Supplier |  |  |  |  | Follow up with supplier |  |  |  | Received Material |  |  |  | Quality and Quantity Check
Who | Purchase Assistant |  |  |  | Jayant |  |  |  |  | Jayant |  |  |  | Gate Incharge |  |  |  | Purchase Assistant
How | ERP |  |  |  | Send Email and Get confirmation and Lead Time |  |  |  |  | Get ETA confirmation on whatsapp |  |  |  | Material Receiving Checklist |  |  |  | Quality and Quentity checklist
When | Whenever Needed |  |  |  | 3 |  |  |  |  | T-2 |  |  |  | T-0 |  |  |  | 2
Timestamp | PO Number | Vendor Name | Quantity | Location | Lead Time | Planned | Actual | Status | Time Delay | Planned | Actual | Status | Time Delay | Planned | Actual | Status | Time Delay | Planned | Actual | Yes/No | Time Delay
2026-05-08 12:43 | 001 | Kajal | 100 | Bangalore | 10 | 2026-05-08 15:43 | 2026-05-08 12:59 | Done |  | 2026-05-16 12:59 |  |  | -4.8831 | 2026-05-18 12:59 |  |  | -6.8831
2026-05-08 14:11 | 002 | moni | 10 | Dhanbad | 1 | 2026-05-08 17:11 | 2026-05-08 14:12 | Done |  | 2026-05-07 14:12 | 2026-05-09 09:53 | Done | 43:41 | 2026-05-09 14:12 |  |  | 49:35
2026-05-08 17:35 | 1 | rajesh | 5000 | ben | 2 | 2026-05-09 12:35 | 2026-05-08 17:35 | Done |  | 2026-05-08 17:35 | 2026-05-08 17:38 | Done | 0:03 | 2026-05-10 17:35 |  |  | 22:12
2026-05-09 09:53 | 003 | vinay | 200 | jharkhand | 4 | 2026-05-09 13:00 | 2026-05-09 09:58 | Done |  | 2026-05-11 09:58 |  |  | 5:50 | 2026-05-13 09:58 |  |  | -1.7573
2026-05-09 10:11 | 004 | moni | 10 | Rajajinagar | 4 | 2026-05-09 13:11 | 2026-05-09 10:35 | Done |  | 2026-05-11 10:35 |  |  | 5:12 | 2026-05-13 10:35 |  |  | -1.7832
Formulas:
Follow up with supplier = IF(AND([Actual]<>"",[Issue PO To Supplier]<>""),[Actual]+[Issue PO To Supplier]-2,"")
Received Material = IF(AND([Actual]<>"",[Issue PO To Supplier]<>""),[Actual]+[Issue PO To Supplier]-0,"")

## Config (hidden)
10:00 | Opening Time
18:00 | Closing Time
0000001 | Working Days (0=working, 1=off; Mon-Sun)