## Form responses 1
Timestamp | Order Number | Customer Name | ITeam Name | Quentity
2026-05-09 10:38 | 001 | Kajal | Watch | 1
2026-05-09 10:45 | 002 | vinay | shoes | 2
2026-05-09 13:43 | 003 | sapna | tumler | 1
2026-05-10 14:30 | 005 | Binita | Phone | 1
2026-05-10 14:38 | 78 | sesharam | fhfgh | 20

## FMS
2026-05-11 15:52
What | Entery Event |  |  |  | Check order |  |  |  | Packing Order |  |  |  | Deliver Order |  |  |  | delivered confirmed ? |  |  |  | Order Closed |  |  |  | Reattempt Delivery
Who | Paresh (sales/admin) |  |  |  | Parkash |  |  |  | Warehouse Staff |  |  |  | Delivery Boy |  |  |  | Delivery boy |  |  |  | Admin |  |  |  | Delivery Boy
How | Order received |  |  |  | Verify customer details, item, quantity |  |  |  | Pick item, pack, label |  |  |  | Delivery to Customer |  |  |  | Take otp |  |  |  | Remark complete order |  |  |  | Retry delivery
When | Whenever Needed |  |  |  | 1 |  |  |  | 1 |  |  |  | 2 |  |  |  | 0.5 |  |  |  | 0 |  |  |  | 1
Timestamp | Order Number | Customer Name | ITeam Name | Quentity | Planned | Actual | Status | Time Delay | Planned | Actual | Status | Time Delay | Planned | Actual | Status | Time Delay | Planned | Actual | Yes/No | Time Delay | Planned | Actual | Status | Time Delay | Planned | Actual | Status | Time Delay
2026-05-09 10:38 | 001 | Kajal | Watch | 1 | 2026-05-09 12:30 | 2026-05-09 11:43 | Done |  | 2026-05-09 12:43 | 2026-05-09 12:03 | Done |  | 2026-05-09 14:03 | 2026-05-09 15:03 | Done | 1:00 | 2026-05-09 15:33 | 2026-05-09 16:42 | Yes | 1:09 | 2026-05-09 16:42 | 2026-05-10 14:19 | Done | 21:38
2026-05-09 10:45 | 002 | vinay | shoes | 2 | 2026-05-09 12:30 |  | Done | 51:22 |  | 2026-05-09 13:46 | Done |  | 2026-05-09 15:46 | 2026-05-09 14:43 | Done |  | 2026-05-09 15:13 | 2026-05-09 16:41 | No | 1:28
2026-05-09 13:43 | 003 | sapna | tumler | 1 | 2026-05-09 14:43 | 2026-05-09 15:03 | Done | 0:21 | 2026-05-09 16:04 | 2026-05-10 14:12 | Done | 22:08 | 2026-05-11 13:30 | 2026-05-10 14:21 | Done |  | 2026-05-11 12:00 | 2026-05-10 14:21 | No
2026-05-10 14:30 | 005 | Binita | Phone | 1 | 2026-05-11 12:30 | 2026-05-10 14:33 | Done |  | 2026-05-11 12:30 | 2026-05-10 14:34 | Done |  | 2026-05-11 13:30 | 2026-05-10 14:35 | Done |  | 2026-05-11 12:00 | 2026-05-10 14:36 | No
2026-05-10 14:38 | 78 | sesharam | fhfgh | 20 | 2026-05-11 12:30 | 2026-05-10 14:41 | Done |  | 2026-05-11 12:30 |  |  | 3:22

## Config (hidden)
11:30 | Opening Time
20:30 | Closing Time
0000001 | Working Days (0=working, 1=off; Mon-Sun)